## 02221-Log
Information Action | Topic | Minutes | PIC | Date Generated | Planned Completion Date | Actual Completion
I | User Logs | The team has discussed the user activity logs | Team | 2021-02-02 | 2021-02-05 | 2021-02-02
I | Attachments | The team has discussed the uploading and downloading of attachments | Team | 2021-02-02 | 2021-02-05 | 2021-02-02
A | User Accounts | Add default password column in blaine intranet database users table | Christian | 2021-02-02 | 2021-02-05 | 2021-02-02
A | User Logs for Update | Research solution for capturing updated information in 201 data | Christian | 2021-02-02 | 2021-02-05
A | Announcement in Login Page | Display top 3 announcement in Login Page | Jesa | 2021-02-02 | 2021-02-05 | 2021-02-04
A | User Accounts | Create user accounts for testers | Jesa | 2021-02-02 | 2021-02-05 | 2021-02-02
A | Blaine Forms | Create user interface and functionality of Blaine Forms | Christian | 2021-02-02 | 2021-02-05 | 2021-02-03
A | 5S Modules | Create user interface and functionality of 5S Module | Jesa | 2021-02-02 | 2021-02-05 | 2021-02-03
A | 5S Module Excel Form | Send 5S Module Excel Form | Vener | 2021-02-02 | 2021-02-05
A | User Accounts Change Password | Create change password functionality for users | Christian | 2021-02-02 | 2021-02-05 | 2021-02-02
A | Blaine Forms and 5S Module | Create workbook for Blaine Forms and 5S Module | Jesa | 2021-02-02 | 2021-02-05 | 2021-02-02
A | Website Interdepartment Minutes | Prepare documents for website closure | Jesa | 2021-02-02 | 2021-02-05 | 2021-02-02
A | Website Feedback Form | Follow up website feedback form from marketing | Christian | 2021-02-02 | 2021-02-05 | 2021-02-02

## 02221-5SBForm
Information Action | Topic | Minutes | PIC | Date Generated | Planned Completion Date | Actual Completion
I | Weekly Meeting | The team has meet to kick start the 5S module and Blaine Forms. | Team | 2021-02-02 | 2021-02-02 | 2021-02-02
A | 5S Module | Send 5S Module Excel Form | Vener | 2021-02-02 | 2021-02-05
A | Blaine Forms Module | Create user interface and functionality of Blaine Forms | Developer | 2021-02-02 | 2021-02-05 | 2021-02-03
A | 5S Module | Create user interface and functionality of 5S Module | Developer | 2021-02-02 | 2021-02-05 | 2021-02-03