## Sheet1
Login and Homepage |  | Target | Done | All
Documentation & Design |  | 100% | 2 | 2
User Interface Proposal
Setting up of Software Requirements
UI: HTML, CSS, JAVASCRIPT |  | 100% | 12 | 13
Login Page
Terms and Conditions
Modals
Login Page Responsiveness
Background Color
Homepage
Quick Links
Departmental Announcement
Alignment and Padding
Page Title Icon
Hover Effects
Icon Links
Homepage Responsiveness
Database Creation: PHP & MySQL |  | 100% | 2 | 3
Login Datatable
Login Configuration
Login PHP Code
HR Module
Documentation & Design |  | 100% | 1 | 1
User Interface Proposal
UI: HTML, CSS, JAVASCRIPT |  | 100% | 9 | 9
Create Page: Text Fields, Dropdowns, Date
Read Page: Viewing of Information per ID Number
Update Page
Delete Page
HR Module Responsiveness
Welcome User Javascript
Quick Links
Ribbon Tabs: Data Viewing, Data Extraction, Printing, Deletion, Data Visualization
HR Menu Buttons
Database Creation: PHP & MySQL |  | 100% | 13 | 15
Database Creation
Datatable Creation: Academe, Attachments, Children Info, Emergency Contact Person, Employment Info, Father Info, Government Mandated ID, Mother Info, Permanent Address, Personal Information, Present Address, Siblings Info, Spouse Info, User Info
Configuration Page Coding
Database Connection Page Coding
Datatable Relationship
ERD Diagram
Create Page: Textfields, Dropdowns, Date
Uploading Attachments: Government Mandated ID, Other Attachments Fields Creation
Uploading Attachments: Folder Creation
Read Page
Information Summary
Information Summary Update
Update Page
Delete Page
Page Restriction: User will be required to log in before navigating the system
Testing & User Acceptance Test
Alpha Testing, Beta Testing & Revision |  | 100% | 0 | 0
Others
Edited Logo used in Blaine Intranet |  | 100% | 2 | 2
Darkmode
Blaine Intranet Desktop Shortcut
Note on D6: Jesa Nina C. Lacambra: For debugging: Modal
Note on D20: Jesa Nina C. Lacambra: For debugging: Database revision - Connection of login and user table
Note on D37: Jesa Nina C. Lacambra: For debugging: Database and View Function

## Sheet2
Login and Homepage
Documentation & Design
| User Interface Proposal | Created user interface design
| Setting up of Software Requirements | Installed and configured all the softwares needed
UI: HTML, CSS, JAVASCRIPT
| Login Page | Front-end coding of login page
| Terms and Conditions | Generated terms and conditions
| Modals | Front-end coding of log-in page modals
| Login Page Responsiveness | Set log-in page to adapt different screen sizes
| Background Color | Set the log in page background color
| Homepage | Front-end coding of homepage
| Quick Links | Front-end coding of quicklinks
| Departmental Announcement | Front-end coding of departmental announcement
| Alignment and Padding | Set the alignment and padding of homepage texts
| Page Title Icon | Added icon of title page
| Hover Effects | Added hover effects to the images
| Icon Links | Added link to the icons
| Homepage Responsiveness | Set homepage to adapt different screen sizes
Database Creation: PHP & MySQL
| Login Datatable | Created datatable for users
| Login Configuration | Configured the login page connection
| Login PHP Code | Back-end coding of login page
HR Module
Documentation & Design
| User Interface Proposal | Created user interface design
UI: HTML, CSS, JAVASCRIPT
| Create Page: Text Fields, Dropdowns, Date | Front-end coding of text fields, dropdowns and date of create page
| Read Page: Viewing of Information per ID Number | Front-end coding of read page wherein information can be view by clicking the ID Number
| Update Page | Front-end coding of update page wherein information can be updated by clicking the ID Number
| Delete Page | Front-end coding of delete button
| HR Module Responsiveness | Set hr module to adapt different screen sizes
Welcome User Javascript
Quick Links
Ribbon Tabs: Data Viewing, Data Extraction, Printing, Deletion, Data Visualization
HR Menu Buttons
Database Creation: PHP & MySQL
Database Creation
Datatable Creation: Academe, Attachments, Children Info, Emergency Contact Person, Employment Info, Father Info, Government Mandated ID, Mother Info, Permanent Address, Personal Information, Present Address, Siblings Info, Spouse Info, User Info
Configuration Page Coding
Database Connection Page Coding
Datatable Relationship
ERD Diagram
Create Page: Textfields, Dropdowns, Date
Uploading Attachments: Government Mandated ID, Other Attachments Fields Creation
Uploading Attachments: Folder Creation
Read Page
Information Summary
Information Summary Update
Update Page
Delete Page
Page Restriction: User will be required to log in before navigating the system
Others
Edited Logo used in Blaine Intranet
Darkmode
Blaine Intranet Desktop Shortcut