## 020821-Log
Information Action | Topic | Minutes | PIC | Date Generated | Planned Completion Date | Actual Completion | Column1 | Column2
A | Table responsiveness | Check and update table responsiveness | Developer | 2021-02-08 | 2021-02-11
A | Text limit | Limit text display in view list | Developer | 2021-02-08 | 2021-02-11
A | Edit status button | Change edit status button to edit remarks | Developer | 2021-02-08 | 2021-02-11
A | Implemented list table | Add category column in implemented list table | Developer | 2021-02-08 | 2021-02-11
A | Implemented list title | Change implemented list title to 5S continuous improvement project | Developer | 2021-02-08 | 2021-02-11
A | Idea owner | Include idea from in adding 5S idea | Developer | 2021-02-08 | 2021-02-11
A | Idea status | Change idea status user interface | Developer | 2021-02-08 | 2021-02-11
A | Database upload | Upload updated 201 database | Developer | 2021-02-08 | 2021-02-11

## 020421-5SBUAT
Information Action | Topic | Minutes | PIC | Date Generated | Planned Completion Date | Actual Completion | Column1 | Column2
I | User testing | The team has presented and tested the user interface and functionality of Project 5S Module | Team | 2021-02-04 | 2021-02-11
A | Retype password textfield | Add retype password textfield in change password function. | Developer | 2021-02-04 | 2021-02-11 |  | Christian | done
A | Main content padding | Adjust main content padding. | Developer | 2021-02-04 | 2021-02-11 |  | Jesa | Done
A | Display of action button | Display action button in table | Developer | 2021-02-04 | 2021-02-11 |  | Jesa | Done
A | Share my idea title | Change share my idea title to 5S share my idea | Developer | 2021-02-04 | 2021-02-11 |  | Jesa | Done
A | Blaine forms attachment name | Remove attachment name field | Developer | 2021-02-04 | 2021-02-11 |  | Christian | done
A | Edit function restriction | Restrict edit button wherein user cannot share other's idea | Developer | 2021-02-04 | 2021-02-11 |  | Christian | done
A | 5S idea list | Change idea list column order | Developer | 2021-02-04 | 2021-02-11 |  | Jesa | Done
A | 5S idea status color coding | Apply color coding to status | Developer | 2021-02-04 | 2021-02-11 |  | Christian | Done
A | 5s idea list view | Display my idea table before user information | Developer | 2021-02-04 | 2021-02-11 |  | Christian | done
A | 5s idea list view | Include attachment in my idea table | Developer | 2021-02-04 | 2021-02-11 |  | Christian | done
A | Blaine forms action button | Adjust action button to be the same with each other | Developer | 2021-02-04 | 2021-02-11 |  | Jesa | Done
A | Blaine forms name | Set blaine forms name to capslock | Developer | 2021-02-04 | 2021-02-11 |  | Christian | done
A | Table csv button | Remove csv button in table | Developer | 2021-02-04 | 2021-02-11 |  | Jesa | Done
A | 5s idea list status | 5s champion can revert back the status to open | Developer | 2021-02-04 | 2021-02-11 |  | Christian
A | 5s idea list control number | Link control number to view function | Developer | 2021-02-04 | 2021-02-11 |  | Jesa | Done
A | 5s idea list view | Include remarks in 5s idea list view | Developer | 2021-02-04 | 2021-02-11 |  | Christian
A | 5s idea list table | Add styling in 5s idea list table | Developer | 2021-02-04 | 2021-02-11 |  | Jesa | done
A | Implemented 5s idea list page | Create implemented 5s idea list page | Developer | 2021-02-04 | 2021-02-11 |  | Jesa
A | 5s idea attachment | Change attachment to be optional only | Developer | 2021-02-04 | 2021-02-11 |  | Christian | done
A | Implemented 5s idea view | Display the before, after and impact in implemented 5s idea view | Developer | 2021-02-04 | 2021-02-11 |  | Jesa | done
A | Implemented 5s idea list page | Add a checkbox button of 5s category wherein the user can filter the list | Developer | 2021-02-04 | 2021-02-11 |  | Jesa

## 02221-Log
Information Action | Topic | Minutes | PIC | Date Generated | Planned Completion Date | Actual Completion
I | User Logs | The team has discussed the user activity logs | Team | 2021-02-02 | 2021-02-05 | 2021-02-02
I | Attachments | The team has discussed the uploading and downloading of attachments | Team | 2021-02-02 | 2021-02-05 | 2021-02-02
A | User Accounts | Add default password column in blaine intranet database users table | Christian | 2021-02-02 | 2021-02-05 | 2021-02-02
A | User Logs for Update | Research solution for capturing updated information in 201 data | Christian | 2021-02-02 | 2021-02-05
A | Announcement in Login Page | Display top 3 announcement in Login Page | Jesa | 2021-02-02 | 2021-02-05 | 2021-02-04
A | User Accounts | Create user accounts for testers | Jesa | 2021-02-02 | 2021-02-05 | 2021-02-02
A | Blaine Forms | Create user interface and functionality of Blaine Forms | Christian | 2021-02-02 | 2021-02-05 | 2021-02-03
A | 5S Modules | Create user interface and functionality of 5S Module | Jesa | 2021-02-02 | 2021-02-05 | 2021-02-03
A | 5S Module Excel Form | Send 5S Module Excel Form | Vener | 2021-02-02 | 2021-02-05
A | User Accounts Change Password | Create change password functionality for users | Christian | 2021-02-02 | 2021-02-05 | 2021-02-02
A | Blaine Forms and 5S Module | Create workbook for Blaine Forms and 5S Module | Jesa | 2021-02-02 | 2021-02-05 | 2021-02-02
A | Website Interdepartment Minutes | Prepare documents for website closure | Jesa | 2021-02-02 | 2021-02-05 | 2021-02-02
A | Website Feedback Form | Follow up website feedback form from marketing | Christian | 2021-02-02 | 2021-02-05 | 2021-02-02

## 02221-5SBForm
Information Action | Topic | Minutes | PIC | Date Generated | Planned Completion Date | Actual Completion
I | Weekly Meeting | The team has meet to kick start the 5S module and Blaine Forms. | Team | 2021-02-02 | 2021-02-02 | 2021-02-02
A | 5S Module | Send 5S Module Excel Form | Vener | 2021-02-02 | 2021-02-05
A | Blaine Forms Module | Create user interface and functionality of Blaine Forms | Developer | 2021-02-02 | 2021-02-05 | 2021-02-03
A | 5S Module | Create user interface and functionality of 5S Module | Developer | 2021-02-02 | 2021-02-05 | 2021-02-03